# TN-011 - Sparing Philosophy and Impacts

Assuming RBSP’s current sparing philosophy, the following is an estimate on approximately how long it would take to troubleshoot, effect repairs and ultimately re-integrate the EFW instrument on the spacecraft. The estimate is based upon the following assumptions:

A) The failure is a single part on any particular assembly within the instrument

B) The failed unit requires the removal of the instrument component from the spacecraft.

C) The component is transported to the instrument facility for troubleshooting and repair.

D) Following the repair, the unit undergoes necessary inspection, re-coating, electrical test, workmanship vibration and thermal testing.

E) The unit is returned to the spacecraft for re-integration.

The time required to complete steps A thru E is highlighted below.

Based upon past experience, we estimate a five week schedule as follows:

[0.2] Component removed, transported to UCB, bench preparations occur;

[0.4] Bench test to verify and document failed condition;

[0.4] Disassembly, inpection, photographs, repair plan developed, FRB;

[1.0] Component replacement, QA inspection, functional test, clean, coat, QA inspect

[1.0] Unit level (IDPU, or SPB) level functional tests or deployments;

[0.4] Workmanship vibration

[1.0] Thermal Vacuum (2 days plus 1 day for each cycle)

[0.6] Transport to APL, Bench test, Integrate, Retest

Board level or other sparing certainly would improve the turn-a-round time significantly.

For the IDPU, board-level sparing would provide the capability to swap out boards at APL.  A failed IDPU card could be replaced in 1 day and the unit returned to the spacecraft the following day.  That part of the sequence could be as short as 3 days including retest. Presumably, the FRB would need to determine the requalification plan depending upon the nature of the failure. Requalification of the unit (vibration and TV) could be defered to a more convenient time and would amount to the following three week schedule:

[1.0] Transport to UCB, Unit level (IDPU) level functional tests;

[0.4] Workmanship vibration

[1.0] Thermal Vacuum (2 days plus 1 day for each cycle)

[0.6] Transport to APL, Bench test, Integrate, Retest

For SPB or AXB general failures, we would replace the units with fully qualified spares.  This would probably take 1-2 working days to remove, replace and retest the electrical connections. Failed units would be returned to UCB for analysis of the failure.  Based upon a component failure, the unit repair/retest sequence would be approximately five weeks detailed above.

In the past, there have been issues handled locally within the I&T environment, and we believe replacement of a sensor cable or motor is possible at APL.  The former was performed on CRRES, for example, after a cable was stepped on by spacecraft technicians.  The SPB is built to be disassembled and cable replaced without disturbing its structural qualifications.  A restow operation does not require a new vibration test, though  a more invasive disassembly would require the unit to be returned to UCB and requalified.

For the AXB, replacement of a sensor is possible at APL.  Any other disassembly would require the unit to be returned to UCB and requalified.